## A845
Revised | 2004-04-02 | v7
Description | Bulk Kit # | Shipping or New Product | Committed Not-Committed | In-Box After Sales Compatibility | Comments | Product Manager | Accessory Launch Packages | Methods of Specification (in Print Room) | Drawings (in Print Room) | Product Folder / Comments
Power Solutions
Battery 800mAh LiIon | SNN5639B | S | Y | In-Box | Reuse of Talon battery | Engstrom |  | 6087651 | 188493
Charger, Desktop | SPN5078A | S | Y | After Sales | Same DTC as for Talon Inegrated | Cecil
Charger, Rapid Travel - US/Thai (F/Blades) | SPN5049A | S | Y | In-Box | Identical to Talon | Cecil | http://compass.mot.com/go/116270413 | 2587514 | 185999
Charger, Rapid Travel - HK | SPN5051A | S | Y | After Sales |  |  | Identical to Talon
Charger, Rapid Travel - PRC | SPN5052A | S | Y | After Sales |  |  | Identical to Talon
klaus adaptor - UK | SYN7455A | S | Y | After Sales |  |  | Identical to Talon
klaus adaptor - Euro | SYN7456A | S | Y | After Sales |  |  | Identical to Talon
klaus adaptor - Aust/NZ | SYN8127A | S | Y | After Sales |  |  | Identical to Talon
In-Vehicle Solutions
Car Kit, Bluetooth Pro Install (US) (EMEA) Hang-Up Cup (HUC) | S9642A S9643A SYN0691B | S S S | Y | After Sales | Same HUC as for Talon Inegrated | Wei | http://compass.mot.com/go/111601328 | User Interface Module - 0187479 Kit - 0187959
Bluetooth Quadrant SpeakerPhone BT Self-Install Car Kit | SYN0736A | S 15 Feb 04 | Y | After Sales | BT Hands-Free Profile Needed | Rauch
Self Install HF Retractable (Razorbill) | SYN0613A | S | Y | After Sales | Identical to Talon | Brandt | http://compass.mot.com/go/116271975 | 187733
Universal Self Install HF (Mandarin) | TBD | S 30 June 04 | Y | After Sales |  | Brandt | http://compass.mot.com/go/116271975 | 187733
Car Kit, Professional Install (Plover) Hang-Up Cup (HUC) | S9950A SYN0691B | S S | Y | After Sales | Same HUC as for Talon Inegrated | Wei | http://compass.mot.com/go/111914102 | Assembly - 0187753 Kit - 0189191
Vehicle Power Adapter (Gadwall) | SYN0707A | S | Y | After Sales |  | Cecil |  | 188958
Audio & Connectivity
3rd Gen Bluetooth Headset (Paladin) | SYN9826A | S | Y | After Sales |  | Zimbric |  |  | 0189110 Not Yet Posted
CLI High-Tier Bluetooth Headset | SYN0868A | N Sept 04 | Y | After Sales | BT Hands-Free Profile Needed BT PAP Profile Preferred | Zimbric
Low-Tier Bluetooth Headset (RipCurl) | SYN0945A | S 29 Apr 04 | Y | After Sales | BT Hands-Free Profile Needed | Zimbric
Headset, FM Stereo | SYN8609B | S | Y | After Sales | Identical to Talon | Downey |  | 189675
Headset, Retractable | SYN8284A | S | Y | Compatibility |  | Downey | http://compass.mot.com/go/108600051 | 189019
Headset, Retractable | SYN9050A | S | Y | After Sales | Identical to Talon | Downey | http://compass.mot.com/go/108599935 | 187401
Headset, One Touch | SYN9351A | S | Y | After Sales | Identical to Talon | Downey | http://compass.mot.com/go/108613088 | 5087977
Headset, One Touch | SYN8419B | S | Y | Compatibility |  | Downey |  | 5089352 | 187774
Mono Headset (black) | SYN8390B | S | Y | After Sales |  | Downey |  | 5009595
Headset, Mono | SYN9350A | S | Y | After Sales | Identical to Talon | Downey | http://compass.mot.com/go/108599634 | 5087977 same as SYN9351A
Mono Headset (silver) | AAYN4264B | S | Y | In-Box |  | Downey |  | 5070371 (A01)
Headset, Over the Ear | SYN8908B | S | Y | After Sales | Identical to Talon | Downey | http://compass.mot.com/go/108610005 | 5088722
Headset, Neck Loop | SYN7875C | S | Y | After Sales | Identical to Talon | Downey | http://compass.mot.com/go/108604876 |  | 189454
Headset, Stereo | SYN0384A | S | Y | In-Box | Identical to Talon | Downey | http://compass.mot.com/go/108599634 | 5088734
Data Cable, USB | SKN6311B | S | Y | After Sales | Identical to Talon | Swambar |  | 3089157
Mobile Phone Tools (MPT) Phase III - USB CE Bus - Mini USB - Bluetooth | TBD | S 7 May 04 | Y | After Sales | The MPT team requires: - SW feature complete, re-flashable phone samples - High resolution images in .eps format for skin development - To realize ALL the features of MPT-3, the phone SW should support: -- SyncML over local transports for PIM data (MRS 8009, 6127) -- OBEX enhancements (MRS 8636) -- Other SW requests (low priority MPT 3 features): --- support for recurring calendar events --- RIM client integration (MRS 9397 | Skelley |  | N/A ??
Bluetooth PC USB Adapter | SYN0717A | S | Y | After Sales |  | Swambar |  | ??
Bluetooth QWERTY Keypad/Keyboard | SYN0939A | N | N | After Sales |  | Swambar
Consumer Personalization
Carrying Case | 3rd Party | New Phone SA | Y | After Sales | 26 Nov - supplied by 3rd party licensees. Need 10 non-functional final plastics 4 months prior to SA. Need 2 functional samples at least 1 month prior to SA for AWS approval | Hrudicka
CPAD is responsible for testing all new accessories denoted by "N". Phone team responsible for testing all Shipping accessories denoted by "S". All CPAD commits are contingent on passing CPAD ERB process.
Phone Team ** All call functional testing done on GSM 1900. Buzz testing done at 900, 1800, and 1900. All functional testing redone on Anritsu (WCDMA)
REMOVED
SD Card, 128MB | 98468H | S | Y | Y | Talon Integrated has an embedded 64 MB SD card. | Swambar |  | 9987773
SD Card, 64MB | 98467H | S | Y | Y | Talon Integrated has an embedded 64 MB SD card. | Swambar |  | 9987772
SD Card, 32MB | 98466H | S | Y | Y | Talon Integrated has an embedded 64 MB SD card. | Swambar |  | ??
Extended Battery 1400+mAh LiIon | SNN5631A | N 28 Aug 03 | Y | In-Box | Double stack of the 4x34x50 cell | Engstrom |  | 6089288
Charger, Rapid Travel - HK | SPN5051A | S | Y | After Sales | Identical to Talon | Cecil |  | same as above
Charger, Rapid Travel - PRC | SPN5052A | S | Y | After Sales | Identical to Talon | Cecil |  | same as above
klaus adaptor - UK | SYN7455A | S | Y | In-Box | Identical to Talon | Cecil |  |  | 2804886
klaus adaptor - Euro | SYN7456A | S | Y | In-Box | Identical to Talon | Cecil |  |  | same as above
klaus adaptor - Aust/NZ | SYN8127A | S | Y | In-Box | Identical to Talon | Cecil |  |  | same as above
Vehicle Power Adapter | SYN7818A | S | Y | Compatibility | Identical to Talon | Downey |  | 2588551
Vehicle Power Adapter | SYN7818B | S | Y | Compatibility |  | Downey |  | 2588551
Headset, Bluetooth (Thor) | SYN9006A | S | Y | Compatibility | Identical to Talon | Zimbric | http://compass.mot.com/go/118018764 | 187920
Headset, Bluetooth (Hammer) | SYN9006B | S | Y | Compatibility | Identical to Talon | Zimbric | http://compass.mot.com/go/118018764 | 187920
PCMCIA Card, Bluetooth | SYN8625A | S | Y | Compatibility |  | Swambar |  | 187313
Charger, Desktop (Low Cost) w/no additional battery slot | SPN5204A | N 31 Mar 04 | Y | After Sales | REMOVED - 10 Dec 03 | Downey
RS 232 Cable | SKN6315B | S | Y | After Sales | REMOVED - 5 Feb 04 Kitted in S9141 / Identical to Talon | Swambar |  | 3089710
Extended Battery 1400+mAh LiIon | SNN5631A | S | Y | After Sales | Removed 4/2/2004. Per A845 team. Not excap battery door will be available.

## Compatibility Test Matrix
Accessory Compatibility Countdown Matrix | [9 empty] | Test Result Validation
Phone Program: | A845 | [8 empty] | Not Started
Tracked S/A Date: | 2004-06-01 | [8 empty] | Started
First Customer Lab Submission: | 2004-05-05 | [8 empty] | Pass
Compatibility Compass Site: | http://compass.mot.com/go/133525939 | [8 empty] | Fail
Compatibility Test Specification: | 12M09192A85 | [8 empty] | N/A
Last Update: | 2004-04-26
By: | Trace Thayer
|  | Contact: | Shawn Jones | Trace Thayer | N/A | N/A | Jeff Marinucci
Description | Bulk Kit # | Shipping or New Product | Phone Team Testing | GNPO Test Status | Audio Testing | System Test Testing | CPAD Test Status | Open CR List | Comments
Power Solutions
Battery 800mAh LiIon | SNN5639B | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Charger, Desktop | SPN5078A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Charger, Rapid Travel - US/Thai (F/Blades) | SPN5049A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Charger, Rapid Travel - HK | SPN5051A | S | N/A | N/A | N/A | N/A | N/A
Charger, Rapid Travel - PRC | SPN5052A | S | N/A | N/A | N/A | N/A | N/A
klaus adaptor - UK | SYN7455A | S | N/A | N/A | N/A | N/A | N/A
klaus adaptor - Euro | SYN7456A | S | N/A | N/A | N/A | N/A | N/A
klaus adaptor - Aust/NZ | SYN8127A | S | N/A | N/A | N/A | N/A | N/A
In-Vehicle Solutions
Car Kit, Bluetooth Pro Install (US) (EMEA) Hang-Up Cup (HUC) | S9642A S9643A SYN0691B | S S S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Bluetooth Quadrant SpeakerPhone BT Self-Install Car Kit | SYN0736A | S 15 Feb 04 | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Self Install HF Retractable (Razorbill) | SYN0613A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Universal Self Install HF (Mandarin) | TBD | N | Not Started | Not Started | N/A | N/A | Not Started |  | GNPO needs sample to test
Car Kit, Professional Install (Plover) Hang-Up Cup (HUC) | S9950A SYN0691B | S S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I) Comments - 1) When a txt message is received, the EM line doesn’t go low when phone alerts. (No requirement to turn on EM with TXT message per Jon Eklund) 2) No HUC used for testing
Vehicle Power Adapter (Gadwall) | SYN0707A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Audio & Connectivity
3rd Gen Bluetooth Headset (Paladin) | SYN9826A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Low-Tier Bluetooth Headset (RipCurl) | SYN0945A | S 29 Apr 04 | Not Started | Not Started | N/A | N/A | Not Started |  | GNPO needs sample to test
Headset, FM Stereo | SYN8609B | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I) "Radio" is not available in the main menu or media center (Radio in main menu is not a requirement per Jon Eklund). Talon Int acted the same way.
Headset, Retractable | SYN8284A | S | Pass | N/A | N/A | N/A | N/A |  | same as syn9350a
Headset, Retractable | SYN9050A | S | Pass | N/A | N/A | N/A | N/A |  | same as syn9350a
Headset, One Touch | SYN9351A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Headset, One Touch | SYN8419B | S | Pass | N/A | N/A | N/A | N/A |  | same as syn9351a
Mono Headset (black) | SYN8390B | S | Pass | N/A | N/A | N/A | N/A |  | same as syn9350a
Headset, Mono | SYN9350A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Mono Headset (silver) | AAYN4264B | S | Pass | N/A | N/A | N/A | N/A |  | same as syn9350a
Headset, Over the Ear | SYN8908B | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Headset, Neck Loop | SYN7875C | S | Pass | N/A | N/A | N/A | N/A |  | No need to test
Headset, Stereo | SYN0384A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Data Cable, USB | SKN6311B | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I)
Mobile Phone Tools (MPT) Phase III - USB CE Bus - Mini USB - Bluetooth | TBD | S 7 May 04 | Not Started | Not Started | N/A | N/A | Pass
Bluetooth PC USB Adapter | SYN0717A | S | Pass | Pass | N/A | N/A | N/A |  | GNPO (74.07.03I) Comments - 1) Did not send or received faxes. 2) Did not connect to the internet - SIM card is not active for the web.3. Audio tones can be heard on the computer's speakers but we do not know how to listen in to music being played on PC.
Consumer Personalization
Carrying Case | 3rd Party | New Phone SA | N/A | N/A | N/A | N/A | Started
| Totals | Pass | 22 | 16 | 0 | 0 | 1 | 39 |  | SA Flags:
|  | Fail | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | GREEN
|  | Not Started | 3 | 3 | 0 | 0 | 2 | 8 |  | 0 | GREEN
|  | Started | 0 | 0 | 0 | 0 | 1 | 1 |  | 1 | RED
|  | % complete | 88% | 84.21% | 0% | 0% | 25% | 81.25% |  | 0 | RED
|  | % started | 88% | 84.21% | 0% | 0% | 50% | 83.33% |  | 1
|  |  | Phone Team Testing | GNPO Test Status | Audio Testing | System Test Testing | CPAD Test Status | Totals |  | 2
|  | Flag: | [7 empty] | Carrier Flags:
Days to SA: | -8092 | RED | [7 empty] | 1 | RED
Days to Carrier Submission: | -8119 | RED | [7 empty] | 0 | GREEN
1
Note: CPAD is responsible for testing all new accessories denoted by "N". Phone team responsible for testing all Shipping accessories denoted by "S".

## Action Items
|  | Revised | 2003-03-26 | v1 |  | Target Dates
Mtg | AI # | Description | Requestor | Owner | Opened | Original | Current | Status/Comments
Active
Monitor
Meetings
Closed

## Notes
CHECKING THIS DOCUMENT IN & OUT OF COMPASS
To avoid overwriting other test teams’ updates, it is critical that everyone follows the Compass check out/in process.
The Check Out process is:
- Login to compass
- Go to the accessory directory where the compatibility matrix is located
- Under the "Functions" heading left mouse click on the "i"
- Select “Check Out/Reserve” – this prevents other users from checking out or saving to the file while it is being updated
- Download the document to your hard drive
- Press "Submit" button
- Make changes to the document (Update current compatibility test status)
The Check In process is:
- Login to compass
- Go to the accessory directory where the compatibility matrix is located
- Under the "Functions" heading left mouse click on the "i"
- Select “Check In / Unreserve”
- Press "Browse" and select the recently updated file from your local drive
- Press "Submit" button
Please note: When making changes, the check out time should be short to minimize the potential for blocking other users from editing the file.
TRACKING TO PHONE S/A DATE:
100% of committed accessories (from PD & CB) must be compatible/ready at phone launch.
Green Trigger Flag:
90 days prior to S/A: >50% testing started
60 days prior to S/A: >80% testing started
30 days prior to S/A: 100% testing started AND >50% testing complete
1 week prior to S/A: 100% testing complete
Red Trigger Flag:
Does not meet the above requirements
TRACKING TO FIRST CUSTOMER SUBMISSION:
All accessories must be submitted to carriers with initial submission.
Green Trigger Flag:
1 week prior to first carrier submission: >95% testing started AND >25% testing complete
Red Trigger Flag:
Does not meet the above requirements
Once the first customer submission is complete, this flag is no longer monitored.